Tips for Addressing Common GPRA Reporting Challenges

SPDG Program Measure 3

Reminder

- Grant year: Counted from the year the SPDG grant was awarded

- Initiative year: Counted from the year that project implementation began

### Measure: The percentage of Special Education State Personnel Development Grant-funded initiatives that meet targets for the use of funds to sustain SPDG-supported practices

### Grantees required to report on the measure: All active grants in initiative years 2 and beyond

#### Tip 1: Review reporting guidance for the measure before entering performance data into the ED 524B Project Status Chart

- The guidance includes information about requirements for the measure, information on how to establish a target, and instructions for reporting data in the Project Status Chart.

#### Tip 2: Establish a target that is appropriate and achievable

- Work with your Project Officer to confirm that your target will not be too difficult or too easy to achieve based on relevant data that are available.

#### Tip 3: Confirm that you are using the correct equation

- Numerator: Cost of technical assistance (TA) activities to sustain use of new skills

- Denominator: Cost of all professional development (PD) activities

Reminder

Project Status Chart Measure Types

- Program: Represents data for a required (GPRA) measure

- Project: Represents data for a measure the project team created

Tip 4: Report complete data in the correct location of the Project Status Chart

- Enter the numerator, denominator, and resulting percentage in the Project Status Chart. There should be enough information so that reviewers can replicate the calculations.

- Confirm that you have entered target data and actual data in the corresponding sections of the Project Status Chart.

#### Sample data in the Project Status Chart

| Performance Measure | Measure Type | Quantitative Data |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| By the end of initiative year 4, 70 percent of SPDG funds will be used for TA activities to sustain the teacher support program | Program | Target |  |  | Actual Performance Data |  |  |
|  |  | Raw Number | Ratio | % | Raw Number | Ratio | % |  |
|  |  |  | 427,350 / 610,500 | 70 |  | 439,560 / 610,500 | - 72 |  |